## Traceability Matrix
Requirement ID | Requirement Description | UC1 | UC2 | UC3 | UC4 | UC5 | Checked
R01 | System to automate the student attendance process (Roll Call) | /
R02 | Instructors can use phone, tablet, or computer to perform Roll Call | /
R03 | Instructors can use a device to perform the Roll Call | /
R04 | Device can be: | /
R04.01 | Phone | /
R04.02 | Tablet | /
R04.03 | Computer | /
R05 | Device must be a Registered Device with AAS | /
R06 | Registered Device must be linked to a Registered Instructor | /
R07 | System shall support multiple instructors | /
R08 | Persist all key data for recovery on demand |  | / | /
R09 | Documentation to be created by Company |  |  |  | /
R09.01 | AAS requirements document |  |  |  | /
R09.02 | AAS design document |  |  |  | /
R09.03 | User Acceptance Tests (UAT) |  |  |  | /
R10 | Persist documentation securely |  |  |  | /
R11 | Documentation available to Client on authorized demand |  |  |  | /
R12 | UAT, if passed, determines contract fulfillment |  |  |  | /
R13 | System should be "big" | / | / | /
R14 | Reports available to authorized users: |  | / | /
R14.01 | Attendance Report | / | /
R14.02 | Student Report |  | /
R14.03 | Course Report |  | /
R15 | CRUD operations for all significant items | / | / | /
R16 | Geolocation support for registered devices | /
R17 | Take student ID pictures via registered device | /
R18 | MySQL database in the cloud |  | / | /
R19 | Access via REST API |  | / | /
R20 | Testing levels: |  |  | / | /
R20.0 | User Acceptance Test (UAT) |  |  | / | /
R20.2 | System Test |  |  | / | /
R20.3 | Unit Testing |  |  | / | /

## Project Plan
Project X: Automated Attendance System - Project Plan
Deadline: May 02, 2025 | [9 empty] | Start Date: March 01, 2025
Task ID | Task Name | Subtask ID | Subtask Name | Deliverables | Assigned To | Estimated Hours | Actual Start Date | Planned Start Date | Actual End Date | Planned End Date | Status | Comments
1 | Project Initiation | 1.1 | Define project objectives | Project scope document | Kristine Mae Bonotan | 1 | 03-21-2025 | 03-21-2025 |  | 03-21-2025 | Done
|  | 1.2 | Project closure & documentation | Stakeholder list | Noncha Tech | 1 | 03-22-2025 | 03-22-2025 |  | 03-22-2025 | Done
|  | 1.3 | Conduct feasibility study | Feasibility report | Kenneth Jay Paragoso | 1 | 03-23-2025 | 03-23-2025 |  | 03-23-2025 | Done
|  | 1.4 | Create project plan | Project plan document | Mike Misoles | 1 | 03-24-2025 | 03-24-2025 |  | 03-24-2025 | Done
|  | 1.5 | Obtain approvals | Approved project charter | Noncha Tech | 1 | 03-25-2025 | 03-25-2025 |  | 03-25-2025 | Done
|  | 2.1 | Gather functional requirements | Requirement specification document | Kenneth Jay Paragoso | 1 | 03-26-2025 | 03-26-2025 |  | 03-26-2025 | Done
2 | Requirements Analysis | 2.2 | Gather non-functional requirements | Performance & security requirements | Mike Misoles | 1 | 03-27-2025 | 03-27-2025 |  | 03-27-2025 | Done
|  | 2.3 | Define system architecture | System architecture diagram | Noncha Tech | 2 | 03-28-2025 | 03-28-2025 |  | 03-29-2025 | Pending
|  | 2.4 | Create wireframes/mockups | UI wireframes | Kristine Mae Bonotan | 2 | 03-30-2025 | 03-30-2025 |  | 03-31-2025 | Pending
|  | 3.1 | Database design | ERD and database schema | Mike Misoles | 3 | 2025-01-04 | 2025-01-04 |  | 2025-03-04 | Pending
3 | Design Phase | 3.2 | API design | API documentation | Noncha Tech | 2 | 2025-04-04 | 2025-04-04 |  | 2025-05-04 | Pending
|  | 3.3 | UI/UX design | Final UI/UX designs | Kenneth Jay Paragoso | 2 | 2025-06-04 | 2025-06-04 |  | 2025-07-04 | Pending
|  | 3.4 | Security design | Security measures document | Kristine Mae Bonotan | 4 | 2025-08-04 | 2025-08-04 |  | 2025-11-04 | Pending
|  | 4.1 | Set up development environment | Configured development tools | Noncha Tech | 1 | 2025-12-04 | 2025-12-04 |  | 2025-12-04 | Pending
|  | 4.2 | Frontend development (React Native) | Initial UI screens | Mike Misoles | 3 | 04-13-2025 | 04-13-2025 |  | 04-15-2025 | Pending
4 | Implementation | 4.3 | Backend development | Working backend APIs | Kenneth Jay Paragoso | 5 | 04-16-2025 | 04-16-2025 |  | 04-20-2025 | Pending
|  | 4.4 | QR Code scanning implementation | Functional QR scanner module | Noncha Tech | 2 | 04-21-2025 | 04-21-2025 |  | 04-22-2025 | Pending
|  | 4.5 | GPS validation implementation | Functional GPS validation | Noncha Tech | 3 | 04-23-2025 | 04-23-2025 |  | 04-25-2025 | Pending
|  | 4.6 | Secure storage implementation | Encrypted storage module | Noncha Tech | 2 | 04-26-2025 | 04-26-2025 |  | 04-27-2025 | Pending
5 | Testing | 4.7 | Testing unit integration | Test reports | Mike Misoles | 1 | 04-28-2025 | 04-28-2025 |  | 04-28-2025 | Pending
|  | 5.1 | Functional testing | Test case reports | Kristine Mae Bonotan | 1 | 04-29-2025 | 04-29-2025 |  | 04-29-2025 | Pending
|  | 5.2 | Security testing | Security vulnerability report | Kenneth Jay Paragoso | 1 | 04-30-2025 | 04-30-2025 |  | 04-30-2025 | Pending
|  | 5.3 | User acceptance testing | User feedback & approval | Mike Misoles | 1 | 2025-01-05 | 2025-01-05 |  | 2025-01-05 | Pending
6 | Deployment | 6.1 | Prepare deployment environment | Deployment guide | Kenneth Jay Paragoso | 1 | 2025-02-05 | 2025-02-05 |  | 2025-02-05 | Pending
|  | 6.2 | Deploy backend API | Hosted backend | Noncha Tech | 2 | 2025-03-05 | 2025-03-05 |  | 2025-04-05 | Pending
|  | 6.3 | Deploy mobile app (beta) | Beta version released | Noncha Tech | 1 | 2025-05-05 | 2025-05-05 |  | 2025-05-05 | Pending
|  | 6.4 | Fix deployment issues | Issue resolution report | Noncha Tech | 3 | 2025-06-05 | 2025-06-05 |  | 2025-08-05 | Pending
7 | Project Demonstration | 6.5 | Release final version | Live mobile app | Mike Misoles | 1 | 2025-09-05 | 2025-09-05 |  | 2025-09-05 | Pending
|  | 7.1 | Prepare presentation materials | Presentation slides | Kristine Mae Bonotan | 1 | 2025-10-05 | 2025-10-05 |  | 2025-10-05 | Pending
|  | 7.2 | Conduct demo for stakeholders | Live demonstration | Noncha Tech | 1 | 2025-11-05 | 2025-11-05 |  | 2025-11-05 | Pending
|  | 7.3 | Gather final feedback | Feedback report | Kenneth Jay Paragoso | 1 | 2025-12-05 | 2025-12-05 |  | 2025-12-05 | Pending
|  | 7.4 | Project closure & documentation | Final project report | Kristine Mae Bonotan | 1 | 05-13-2025 | 05-13-2025 |  | 05-13-2025 | Pending